DIRTYSNATCHA RECORDS

MASTER OPERATIONS PACKAGE

Take Me To Your Leader Tour 2026

"Drugs In Da Club" DSP Campaign

Generated: March 1, 2026

Prepared by: DirtySnatcha Records Command Center

# CRITICAL PATH — NEXT 7 DAYS

The following actions must be completed between March 1-7, 2026. These are ordered by urgency and impact.

| Action | Deadline | Owner | Notes |
| --- | --- | --- | --- |
| Send ABQ promoter email | March 1 | Thomas | Contract + set times + deposit |
| Launch Spotify Save ads ($50-100) | March 1 | Thomas | Push save ratio >10% |
| Post ABQ urgency content | March 1 | Lee/Thomas | "ABQ THIS FRIDAY" post |
| Launch Shazam Spike ABQ ($50-75) | March 2 | Thomas | Regional trending hack |
| Send Tampa promoter email | March 1 | Thomas | Get venue name |
| Send Pittsburgh email (deposit OVERDUE) | March 1 | Thomas | $1,250 deposit past due |
| Execute all 9 DSP hacks | March 1-3 | Lee | See checklist |
| Send KY promoter emails | March 3 | Thomas | Louisville + Covington |
| Follow up with Julian | March 5 | Thomas | Asbury Park + Hartford |
| Begin Tampa/PGH content push | March 8 | Content | Week 2 Final Push |

# TOUR GRID — ALL 16 ACTIVE SHOWS

Total guaranteed income: $38,600 across 16 active shows (Lincoln completed). Budget column shows recommended DirtySnatcha-side Shazam Spike ad spend per show.

| Date | City | Venue | Offer | Phase | Sellout | Ad $ |
| --- | --- | --- | --- | --- | --- | --- |
| 3/6 | Albuquerque, NM | Effex | $2,000 | FINAL PUSH | Med-High | $50-75 |
| 3/13 | Tampa, FL | TBD | $2,000 | FINAL PUSH | Med-High | $50-75 |
| 3/14 | Pittsburgh, PA | SideQuest | $2,500 | FINAL PUSH | High | $50-75 |
| 3/27 | Louisville, KY | TBD | $1,250 | MAINTENANCE | Medium | $50-75 |
| 3/28 | Covington, KY | TBD | $1,250 | MAINTENANCE | Medium | Combined |
| 4/3 | Las Vegas, NV | Ravehouse | $2,000 | ON-SALE | Med-High | $75-100 |
| 4/9 | Denver, CO | Larimer Lounge | $1,500 vs | ON-SALE | Very High | $0-50 |
| 4/11 | Rochester, NY | TBD | $2,000 | ON-SALE | Medium | $50-75 |
| 4/18 | Tucson, AZ | TBD | $1,600 | ON-SALE | Medium | $50-75 |
| 4/24 | Asbury Park, NJ | House of Ind. | $2,500 | ANNOUNCEMENT | Med-High | $50-75 |
| 4/25 | Hartford, CT | Webster Theater | $2,500 | ANNOUNCEMENT | Med-High | $50-75 |
| 5/2 | Butte, MT | Covellite | $5,000 | ANNOUNCEMENT | High | $50-75 |
| 5/15 | OKC, OK | Bamboo Lounge | $2,000 | ANNOUNCEMENT | Medium | $50-75 |
| 5/16 | Dallas, TX | TBD (IM Supp) | $2,000 | ANNOUNCEMENT | N/A | $0 |
| 5/22 | Houston, TX | TBD (IM Supp) | $2,000 | ANNOUNCEMENT | N/A | $0 |
| 6/20 | San Diego, CA | TBD | $3,000 | ANNOUNCEMENT | Medium | $50-75 |

# DSP ALGORITHMIC HACKS — WEEK 1 ACTIONS

"Drugs In Da Club" is 2 days old. The first 7 days determine permanent algorithmic placement. 7 of 9 actions are free. Total cost: $100-175.

## Spotify

- Toggle Discovery Mode ON (free — trades ~30% royalty rate for 2-3x algorithmic impressions)

- Upload Canvas (3-8 sec loop) + Clips (30-60 sec commentary)

- Launch Meta save campaign: $50-100 over 7 days targeting bass music fans in tour markets

- Target: push save-to-stream ratio above 10% to trigger Discover Weekly / Release Radar

- Current Popularity Index: 28 (target: 40+)

## Apple Music

- Launch Shazam Spike: $50-75 geo-targeted ads in Albuquerque (March 2-5)

- Record Artist Message (voice note to Apple Music followers)

- Goal: trigger regional "Trending on Shazam" alert which feeds Apple Music algorithm

## YouTube

- Create 3-5 Shorts using track audio with SEO titles

- Audio re-use by others is the #1 signal for YouTube algorithm

- Check OAC (Official Artist Channel) unification status

## Pandora

- Set "Drugs In Da Club" as Featured Track in Pandora AMP (runs 8 weeks)

- Record Artist Audio Message (15-30 sec tour/track promo)

- Warning: Pandora is extremely ruthless — early thumbs-down permanently deprioritizes

## TikTok

- Post 2-3 TikToks with SEO-optimized titles ("heavy bass drop 2026 dubstep")

- Make audio available as a Sound for re-use

- Ask support artists to post using the audio

## SoundCloud

- Share to Bass Heads FB group for strong first-100 engagement

- Ask for comments specifically (heaviest engagement signal)

- Repost from DirtySnatcha Records label account

## Amazon Music

- Add Alexa CTA to social posts: "Hey Alexa, play Drugs In Da Club by DirtySnatcha"

- Confirm lyrics synced in Musixmatch for voice search matching

# RELEASE CADENCE — DECAY PREVENTION

No new ISRC every 6-8 weeks = Spotify Artist Quality Score decays. DirtySnatcha needs a release every 6 weeks minimum.

Last release: "Drugs In Da Club" (February 27, 2026)

Decay deadline: ~April 10, 2026 (6 weeks)

Next release must be locked by March 6, uploaded to VMG by March 10, and pitched to Spotify editorial by March 27 for an April 10 drop.

2026 minimum releases needed: 7 (one every 6 weeks through December)

Waterfall strategy: Singles released individually, then bundled into EP with same ISRCs in new UPC. EP inherits all accumulated Track Quality Scores from singles.

# AD BUDGET SUMMARY

Total recommended DirtySnatcha-side ad spend for entire tour:

| Category | Budget | Notes |
| --- | --- | --- |
| Shazam Spike Campaigns (14 shows) | $750-1,050 | $50-75/show |
| Spotify Radio Priming (Save Ads) | $100-200 | Ongoing |
| Per-Show Retargeting (if data) | $0-100/show | Pixel-dependent |
| TOTAL | $850-1,350 | Entire tour |

Note: Promoter marketing budgets are separate and required per show agreement. DirtySnatcha budget is supplemental, focused on algorithmic hacks and retargeting.

# DELIVERABLES INCLUDED IN THIS PACKAGE

- ABQ Final Push Social Content (7 ready-to-post captions, March 1-7)

- Tampa + Pittsburgh Final Push Content (14 ready-to-post captions, March 8-15)

- 4-Week Social Content Calendar (March 1-28, all platforms)

- ABQ Shazam Spike Ad Campaign Specs (Meta Ads Manager ready)

- Spotify Radio Priming Ad Campaign Specs (Meta Ads Manager ready)

- Promoter Follow-Up Emails (9 emails, prioritized by urgency)

- Tour Marketing Playbook (all 16 shows with per-show action items)

- DSP Hack Execution Checklist (printable one-pager)

- Release Cadence Framework (6-week cycle, waterfall strategy)

- DSP Algorithmic Hacker Dashboard (interactive React artifact)

- DSR Command Center Dashboard (interactive React artifact)

All documents generated March 1, 2026 by the DirtySnatcha Records Command Center.