## Master Show Grid
# | Date | City | ST | Venue | Offer ($) | Deal Type | Deposit ($) | Deposit % | Deposit Due | Deposit Status | Final Payment Due | Contract Status | Phase (3/2) | Days Out | Promoter | Promoter Email | Promoter Phone | Agent | Support Artists | Ticket Link | Marketing Budget | Sellout Prob | Notes / Action Items
1 | 02/27/2026 | Lincoln | NE | Royal Grove | 2000 | Flat |  |  |  | RECEIVED | SETTLED | ✅ SIGNED | COMPLETED | Past | Lance Dunlap / Royal Grove | lance@globaldance.us |  | Colton/PRYSM | WHOiSEE, Dark Matter, GriG | N/A | N/A | DONE | COMPLETED 2/27. Request final attendance + photos from Sarah Barta (sarahbarta@theroyalgrove.com). Settlement pending.
2 | 03/06/2026 | Albuquerque | NM | Effex | 2000 | Flat | 500 | 25% | PAST DUE | ⚠️ PARTIAL ($500) | Day of show | ❌ NOT SIGNED | FINAL PUSH | 4 | Black Sheep Presents | blacksheeppresents@gmail.com |  | Colton/PRYSM | Mport, Kotrax, HVRCRFT | ❓ | $1,000 Meta (50% co-spend) | Med-High | 🔴 4 DAYS OUT. Contract NOT signed. Only partial deposit ($500). Promoter sent promo video 3/1 — pushing ads. URGENT: Get contract signed + remaining deposit TODAY.
3 | 03/13/2026 | Tampa | FL | TBD ⚠️ | 2000 | Flat | 800 | 40% | PAST DUE | ⚠️ $800 PAID | Day of show | ❌ NOT SIGNED | FINAL PUSH | 11 | C Chur | cre_chur@yahoo.com |  | Colton/PRYSM | Kotrax, Mport, HVRCRFT | Ticket update images sent 2/27 | Spring Break angle | Med-High | 🔴 VENUE STILL TBD. Contract not signed. $800 deposit paid. Ticket update images received from promoter 2/27 — need to review. Spring Break weekend = massive potential but NO VENUE NAME kills marketing.
4 | 03/14/2026 | Pittsburgh | PA | SideQuest | 2500 | Flat | 1250 | 50% | 30 days out (2/12) — OVERDUE | 🔴 OVERDUE | Day of show | ❌ NOT SIGNED | FINAL PUSH | 12 | TBD | TBD |  | Colton/PRYSM | WHOiSEE, Dark Matter | ❓ | Final Push ads 3/1-3/14 | High | 🔴 DEPOSIT OVERDUE. Was due 2/12. $1,250 NOT received. Contract not signed. 12 days out. Need promoter contact info. WHOiSEE + Dark Matter strong draws.
5 | 03/27/2026 | Louisville | KY | TBD ⚠️ | 1250 | Flat |  |  | TBD | ❌ NONE | TBD | ❌ Sent 2/12 | MAINTENANCE → ON-SALE | 25 | TBD | TBD |  | Colton/PRYSM | TBD (rec: Dark Matter/Kotrax) | ❌ None | Combined w/ Covington | Medium | 🟡 Venue TBD. No deposit. Contract sent 2/12 — not returned. Back-to-back with Covington. Need venue name for marketing ASAP.
6 | 03/28/2026 | Covington | KY | TBD ⚠️ | 1250 | Flat |  |  | TBD | ❌ NONE | TBD | ❌ Sent 2/13 | MAINTENANCE → ON-SALE | 26 | TBD | TBD |  | Colton/PRYSM | TBD | ❌ None | Combined w/ Louisville | Medium | 🟡 Venue TBD. No deposit. Contract sent 2/13 — not returned. Paired with Louisville.
7 | 04/03/2026 | Las Vegas | NV | Ravehouse | 2000 | Flat |  |  | TBD | ❓ UNKNOWN | TBD | ❓ UNCLEAR | ON-SALE | 32 | TBD | TBD |  | Colton/PRYSM | HVRCRFT, Mport | ❓ | DFT tie-in angle | Med-High | 🟡 Announce by 3/17. Contract status unclear. Deposit status unknown. Dancefestopia tie-in is key marketing angle. Need promoter contact.
8 | 04/09/2026 | Denver | CO | Larimer Lounge | 1500 | $1,500 vs 90% NET |  |  | TBD | ❓ UNKNOWN | TBD | ❓ UNCLEAR | ON-SALE | 38 | TBD | TBD |  | Colton/PRYSM | Kotrax, Ozztin (local) | ✅ Announced 1/12 | $0-50 Shazam (sells itself) | VERY HIGH | Announced 1/12. Expected sellout. $1,500 vs 90% NET — likely to earn more than guarantee. Both support acts are Denver-local = zero travel cost. Get weekly ticket count from promoter.
9 | 04/11/2026 | Rochester | NY | TBD ⚠️ | 2000 | Flat + hotel reimburse after 175 |  |  | TBD | ❌ NONE | TBD | ❌ NOT SIGNED | ON-SALE | 40 | TBD | TBD |  | MPORT routing | MPORT TMTYL routing | ❓ | $50-75 Shazam | Medium | 🟡 Venue TBD. Hotel reimbursement triggers after 175 tickets sold. Radius clause — need details confirmed by 3/10.
10 | 04/18/2026 | Tucson | AZ | TBD ⚠️ | 1600 | Flat + bonus structure |  |  | TBD | ❓ UNKNOWN | TBD | ❓ UNCLEAR | ON-SALE | 47 | Tyler Hampton / Hiatus Events | hiatusevents@gmail.com |  | AB Touring | TBD | 21 sold / 229 remaining (Eventbrite 3/2) | $50-75 Shazam | Medium | Eventbrite name: "DirtySnatcha in the DirtyT". 21 tickets sold as of 3/2 (229 remaining). Tyler Hampton runs daily Eventbrite updates. AB Touring route — confirm bonus structure with Andrew. Need venue name by 3/20.
11 | 04/24/2026 | Asbury Park | NJ | House of Independents | 2500 | Flat |  |  | TBD | ❌ NONE | TBD | ❌ NOT SIGNED | ON-SALE | 53 | Julian (last name TBD) | TBD |  | TBD | WHOiSEE, Dark Matter | ❌ | TBD | Med-High | 🟡 Spoke to Julian 2/10 re: marketing + deposit. No follow-up received. Back-to-back with Hartford. NYC crossover potential.
12 | 04/25/2026 | Hartford | CT | Webster Theater | 2500 | Flat |  |  | TBD | ❌ NONE | TBD | ❌ NOT SIGNED | ON-SALE | 54 | Julian (same as AP) | TBD |  | TBD | Dark Matter, HVRCRFT | ❌ | TBD | Med-High | 🟡 Same promoter as Asbury Park. No contract or deposit. Underserved CT bass demographic.
13 | 05/02/2026 | Butte | MT | Covellite Theatre | 5000 | $5,000 + travel |  |  | TBD | ❓ UNKNOWN | TBD | ❓ UNCLEAR | ANNOUNCEMENT | 61 | Nick Tortora / Summit Sound | nick@summitsoundproductions.com | 212-390-8589 | Colton/PRYSM | Kotrax, Ozztin, HVRCRFT | Eventbrite page built | MAD Series show | High | 🟡 Highest guarantee on tour. Nick Tortora requesting tech rider (email 3/2). Eventbrite page built 2/17. Need deposit amount/date confirmed. MAD Series = guaranteed audience.
14 | 05/15/2026 | Oklahoma City | OK | Bamboo Lounge | 2000 | Flat |  |  | TBD | ❓ UNKNOWN | TBD | ❓ UNCLEAR | ANNOUNCEMENT | 74 | TBD | TBD |  | TBD | TBD | ❌ | Needs local promo groups | Medium | Need promoter contact, contract status, deposit info.
15 | 05/16/2026 | Dallas | TX | TBD ⚠️ | 2000 | Support slot (Infected Mushroom) |  |  | TBD | ❓ UNKNOWN | TBD | ❓ UNCLEAR | ANNOUNCEMENT | 75 | Andrew Winters / Galaxy Station | AndrewWinters@live.com | 469-473-8987 | Colton/PRYSM | N/A (support slot) | ❓ | No DSR spend needed (headliner draws) | High | Support for Infected Mushroom. Galaxy Station copro with Imagen Concerts (Sirus Ferdows). Colton updated contract info 3/2 — "should be all set now." Venue TBD.
16 | 05/22/2026 | Houston | TX | Escapade Houston | 2000 | $2,000 + HGR |  |  | Per PRYSM: before announcement | ❓ UNKNOWN | TBD | ⚠️ Copro — needs 2 signatures | ANNOUNCEMENT | 81 | Andrew Winters + Sirus Ferdows (Imagen Concerts) | AndrewWinters@live.com / yana@galaxystationevent.com | 469-473-8987 | Colton/PRYSM + Alyssa Lince | N/A (support slot — Special Guest) | ❓ | No DSR spend needed | High | Support slot — Special Guest billing. Copro: Imagen Concerts + Galaxy Station LLC. Contract needs 2 signatories. Colton says "all set" as of 3/2. Andrew Winters wants to announce by Wed 3/4. VENUE CONFIRMED: Escapade Houston. 1 hour set.
17 | 06/20/2026 | San Diego | CA | TBD ⚠️ | 3000 | Flat |  |  | TBD | ❓ UNKNOWN | TBD | ❓ UNCLEAR | ANNOUNCEMENT | 110 | TBD | TBD |  | TBD | TBD | PeerPop link live | Long runway — summer date | Medium | Long runway. PeerPop link already live. Venue TBD. Oakland 6/19 inquiry for Lumberjvck collab (Camila@abtouring.com confirmed date open for HVRCRFT).
NEW | TBD (7/3-4, 7/10-11, or 7/17-18) | Austin | TX | The Courtyard | 2000 | $2K guar (25% dep) + $500 bonus tiers @ 350/450/500/550 tix ($4K walkout) | 500 | 25% | TBD | ⏳ NEW OFFER | TBD | ⏳ OFFER STAGE | OFFER RECEIVED | 120-135 | MAD Series (via AB Touring) | andrew@abtouring.com | (814) 602-5613 | Andrew Lehr / AB Touring | MPORT (promoter trying for) | N/A | TBD | TBD | 🆕 NEW OFFER from Andrew 3/1. $2K guarantee + $500 bonus tiers ($4K walkout potential). $150 hotel/ground buyout + rider. PDF attached to email — NEED TO READ. 3 target date windows. Evaluate against July calendar.
NEW | 08/08/2026 | Rappin The Rivers | TBD | Festival | TBD | TBD |  |  | TBD | ⏳ NEW OFFER | TBD | ⏳ Contract sent by Brandon Pas 3/2 — attachment missing initially, resent | OFFER RECEIVED | 159 | Nichol Barney | nicholeltonbarney@hotmail.com |  | Brandon Pas / PRYSM (brandon@prysmtalentagency.com, 734-695-0617) | TBD | N/A | TBD | TBD | 🆕 NEW. Brandon Pas sent contract 3/2 but attachment was missing. Nichol Barney resent w/ screenshot. Contract PDF "Prysm+Talent+Agency+Contract+for+DirtySnatcha+8-8-26" now attached. NEED TO REVIEW CONTRACT + OFFER DETAILS.

## Deposit & Payment Tracker
# | City | Date | Guarantee | Deposit % | Deposit $ | Deposit Due | Deposit Status | Days Overdue | Final Payment Due | Final Status | Total Received | Outstanding | Action Required
1 | Lincoln | 02/27 | $2,000 | — | — | N/A | ✅ SETTLED | — | N/A | ✅ SETTLED | $2,000 | $0 | Request final attendance count + photos
2 | Albuquerque | 03/06 | $2,000 | 25% | $500 | PAST DUE | ⚠️ PARTIAL ($500 received) | 30+ days | Day of show | ❌ Pending | $500 | $1,500 | 🔴 GET REMAINING $500 + CONTRACT TODAY
3 | Tampa | 03/13 | $2,000 | 40% | $800 | PAST DUE | ⚠️ $800 PAID | ? | Day of show | ❌ Pending | $800 | $1,200 | 🔴 Verify deposit terms. Get venue name. Contract.
4 | Pittsburgh | 03/14 | $2,500 | 50% | $1,250 | 2/12/2026 | 🔴 OVERDUE | 18+ days | Day of show | ❌ Pending | $0 | $2,500 | 🔴 CRITICAL — $1,250 overdue since 2/12. Escalate NOW.
5 | Louisville | 03/27 | $1,250 | TBD | TBD | TBD | ❌ NO DEPOSIT | N/A | TBD | ❌ | $0 | $1,250 | 🟡 Contract sent 2/12. No response. Follow up.
6 | Covington | 03/28 | $1,250 | TBD | TBD | TBD | ❌ NO DEPOSIT | N/A | TBD | ❌ | $0 | $1,250 | 🟡 Contract sent 2/13. No response. Follow up.
7 | Las Vegas | 04/03 | $2,000 | TBD | TBD | TBD | ❓ UNKNOWN | N/A | TBD | ❓ | ? | ? | 🟡 Verify contract + deposit status. Announce by 3/17.
8 | Denver | 04/09 | $1,500 vs 90% | TBD | TBD | TBD | ❓ UNKNOWN | N/A | TBD | ❓ | ? | ? | Likely sellout. Get deposit confirmation.
9 | Rochester | 04/11 | $2,000 | TBD | TBD | TBD | ❌ NO DEPOSIT | N/A | TBD | ❌ | $0 | $2,000 | 🟡 Need venue, contract, deposit info.
10 | Tucson | 04/18 | $1,600 | TBD | TBD | TBD | ❓ UNKNOWN | N/A | TBD | ❓ | ? | ? | 21 tix sold. Confirm bonus structure with Andrew.
11 | Asbury Park | 04/24 | $2,500 | TBD | TBD | TBD | ❌ NO DEPOSIT | N/A | TBD | ❌ | $0 | $2,500 | 🟡 Follow up with Julian from 2/10 call.
12 | Hartford | 04/25 | $2,500 | TBD | TBD | TBD | ❌ NO DEPOSIT | N/A | TBD | ❌ | $0 | $2,500 | 🟡 Same promoter as Asbury Park.
13 | Butte | 05/02 | $5,000+travel | TBD | TBD | TBD | ❓ UNKNOWN | N/A | TBD | ❓ | ? | ? | Nick requesting tech rider 3/2. Highest guarantee.
14 | OKC | 05/15 | $2,000 | TBD | TBD | TBD | ❓ UNKNOWN | N/A | TBD | ❓ | ? | ? | Need promoter contact info.
15 | Dallas | 05/16 | $2,000 | TBD | TBD | TBD | ❓ UNKNOWN | N/A | TBD | ❓ | ? | ? | Support slot. Galaxy Station copro.
16 | Houston | 05/22 | $2,000+HGR | Per PRYSM | Before announce | Before announce | ❓ UNKNOWN | N/A | TBD | ❓ | ? | ? | Copro. Colton says "all set" 3/2. Confirm deposit.
17 | San Diego | 06/20 | $3,000 | TBD | TBD | TBD | ❓ UNKNOWN | N/A | TBD | ❓ | ? | ? | PeerPop link live. Long runway.

## Promoter & Contact Directory
Show | City | Promoter/Org | Contact Name | Email | Phone | Role | Last Contact | Notes
Lincoln (DONE) | Lincoln, NE | Royal Grove / Global Dance | Lance Dunlap | lance@globaldance.us |  | Promoter | 3/1 | Show completed. Settlement pending.
Lincoln (DONE) | Lincoln, NE | Royal Grove | Sarah Barta | sarahbarta@theroyalgrove.com | (402) 577-1509 | Venue | 2/27 | Sent advance PDF. Has photos/videos.
Albuquerque | ABQ, NM | Black Sheep Presents | Black Sheep | blacksheeppresents@gmail.com |  | Promoter | 3/1 | Sent promo video 3/1. Pushing targeted ads.
Albuquerque | ABQ, NM | Voltron Cicada Productions |  | voltroncicada@gmail.com |  | Co-promoter? | 3/1 | CC'd on ABQ thread.
Tampa | Tampa, FL |  | C Chur | cre_chur@yahoo.com |  | Promoter | 2/27 | Sent ticket update images 2/27. Replied 3/2 "Thank you."
Pittsburgh | Pittsburgh, PA | SideQuest | TBD | TBD |  | Promoter |  | 🔴 NO CONTACT INFO. Deposit overdue.
Louisville | Louisville, KY | TBD | TBD | TBD |  | Promoter | 2/12 | Contract sent 2/12. No response.
Covington | Covington, KY | TBD | TBD | TBD |  | Promoter | 2/13 | Contract sent 2/13. No response.
Las Vegas | Las Vegas, NV | Ravehouse | TBD | TBD |  | Promoter |  | Announce by 3/17 per contract.
Denver | Denver, CO | Larimer Lounge | TBD | TBD |  | Promoter | 1/12 | Announced 1/12. Expected sellout.
Rochester | Rochester, NY | TBD | TBD | TBD |  | Promoter |  | MPORT TMTYL routing. Venue TBD.
Tucson | Tucson, AZ | Hiatus Events | Tyler Hampton | hiatusevents@gmail.com |  | Promoter | 3/2 | Daily Eventbrite updates. 21 sold.
Asbury Park | Asbury Park, NJ | House of Independents | Julian | TBD |  | Promoter | 2/10 | Spoke 2/10 re: marketing + deposit.
Hartford | Hartford, CT | Webster Theater | Julian (same) | TBD |  | Promoter | 2/10 | Same promoter as Asbury Park.
Butte | Butte, MT | Summit Sound / MAD Series | Nick Tortora | nick@summitsoundproductions.com | 212-390-8589 | Promoter | 3/2 | Requesting tech rider 3/2. Eventbrite built.
OKC | OKC, OK | Bamboo Lounge | TBD | TBD |  | Promoter |  | No contact info.
Dallas | Dallas, TX | Galaxy Station LLC | Andrew Winters | AndrewWinters@live.com | 469-473-8987 | Promoter/Partner | 3/2 | Copro w/ Imagen. Wants announce by Wed.
Dallas | Dallas, TX | Imagen Concerts | Sirus Ferdows |  |  | Co-promoter/CEO | 2/18 | Copro signatory.
Houston | Houston, TX | Galaxy Station + Imagen | Andrew Winters | AndrewWinters@live.com | 469-473-8987 | Promoter | 3/2 | Copro. Escapade Houston. $2K+HGR.
Houston | Houston, TX | Galaxy Station | Yana | yana@galaxystationevent.com |  | Admin
San Diego | San Diego, CA | TBD | TBD | TBD |  | Promoter |  | PeerPop link live.
Austin (NEW) | Austin, TX | MAD Series (via AB Touring) | Andrew Lehr | andrew@abtouring.com | (814) 602-5613 | Agent/Offer | 3/1 | New offer 3/1. $2K + bonus tiers. PDF attached.
Rappin Rivers (NEW) | TBD | PRYSM | Brandon Pas | brandon@prysmtalentagency.com | 734-695-0617 | Agent | 3/2 | Contract sent 3/2. Initially no attachment.
Rappin Rivers (NEW) | TBD |  | Nichol Barney | nicholeltonbarney@hotmail.com |  | Promoter? | 3/2 | Forwarded screenshot.
— AGENT — |  | AB Touring | Andrew Lehr | andrew@abtouring.com | (814) 602-5613 | Primary Booking Agent | Active
— AGENT — |  | AB Touring | Camila Giudice | camila@abtouring.com |  | Agent | 2/27 | HVRCRFT booking. Oakland 6/19 inquiry.
— AGENT — |  | PRYSM Talent Agency | Colton Anderson | colton@prysmtalentagency.com | 734-904-0224 | Legacy Agent / CEO | Active | O: 810-299-2113
— AGENT — |  | PRYSM Talent Agency | Alyssa Lince | alyssa@prysmtalentagency.com |  | Agent | 1/7 | Houston confirmation.
— AGENT — |  | PRYSM Talent Agency | Brandon Pas | brandon@prysmtalentagency.com | 734-695-0617 | Agent | 3/2 | Rappin Rivers contract.