DIRTYSNATCHA — TAKE ME TO YOUR LEADER TOUR 2026

RECALIBRATED TOUR STATUS REPORT

As of: Sunday, March 1, 2026  |  17 Confirmed Shows  |  Tour Total: ~$38,600 Guaranteed

# Phase Summary

COMPLETED: 1   |   FINAL PUSH: 3 (Albuquerque, Tampa, Pittsburgh)   |   MAINTENANCE: 2 (Louisville, Covington)   |   ON-SALE: 6   |   ANNOUNCEMENT: 5

# Full Tour Grid — Recalibrated Phases

| # | Date | City | ST | Venue | Offer | Phase | Days Out | Recommended Support |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 02/27/2026 | Lincoln | NE | Royal Grove | $2,000 | COMPLETED | Past | WHOiSEE, Dark Matter |
| 2 | 03/06/2026 | Albuquerque | NM | Effex | $2,000 | FINAL PUSH | 5d — URGENT | Mport, Kotrax, HVRCRFT |
| 3 | 03/13/2026 | Tampa | FL | TBD | $2,000 | FINAL PUSH | 12d — URGENT | Kotrax, Mport, HVRCRFT |
| 4 | 03/14/2026 | Pittsburgh | PA | SideQuest | $2,500 | FINAL PUSH | 13d — URGENT | WHOiSEE, Dark Matter |
| 5 | 03/27/2026 | Louisville | KY | TBD | $1,250 | MAINTENANCE | 26d | TBD |
| 6 | 03/28/2026 | Covington | KY | TBD | $1,250 | MAINTENANCE | 27d | TBD |
| 7 | 04/03/2026 | Las Vegas | NV | Ravehouse | $2,000 | ON-SALE | 33d | HVRCRFT, Mport |
| 8 | 04/09/2026 | Denver | CO | Larimer Lounge | $1,500 | ON-SALE | 39d | Kotrax, Ozztin |
| 9 | 04/11/2026 | Rochester | NY | TBD | $2,000 | ON-SALE | 41d | TBD |
| 10 | 04/18/2026 | Tucson | AZ | TBD | $1,600 | ON-SALE | 48d | TBD |
| 11 | 04/24/2026 | Asbury Park | NJ | House of Independents | $2,500 | ON-SALE | 54d | WHOiSEE, Dark Matter |
| 12 | 04/25/2026 | Hartford | CT | Webster Theater | $2,500 | ON-SALE | 55d | Dark Matter, HVRCRFT |
| 13 | 05/02/2026 | Butte | MT | Covellite Theatre | $5,000 | ANNOUNCEMENT | 62d | Kotrax, Ozztin, HVRCRFT |
| 14 | 05/15/2026 | Oklahoma City | OK | Bamboo Lounge | $2,000 | ANNOUNCEMENT | 75d | TBD |
| 15 | 05/16/2026 | Dallas | TX | TBD | $2,000 | ANNOUNCEMENT | 76d | N/A (support slot) |
| 16 | 05/22/2026 | Houston | TX | TBD | $2,000 | ANNOUNCEMENT | 82d | N/A (support slot) |
| 17 | 06/20/2026 | San Diego | CA | TBD | $3,000 | ANNOUNCEMENT | 111d | TBD |

# Immediate Priority Actions

These are the actions required THIS WEEK based on the recalibrated timeline.

| Action | Details | Deadline |
| --- | --- | --- |
| ABQ Final Push Ads | Launch Meta campaign. 5 days out. $1,000 budget (50% of promoter co-spend estimate). Geo: ABQ +50mi. Copy: urgency/last tickets. | NOW — by 3/2 |
| Tampa Maintenance → Final Push | Begin maintenance ads now. Transition to Final Push on 3/1. Geo: Tampa +50mi. Spring Break angle. | 3/1 → 3/13 |
| Pittsburgh Final Push Prep | Show is 3/14. Begin Final Push ads 3/1. WHOiSEE + Dark Matter are strong draws. SideQuest venue. | 3/1 → 3/14 |
| Louisville/Covington On-Sale | 26 days out. On-Sale campaign should be active NOW. Back-to-back KY dates need coordinated push. | Active NOW |
| Las Vegas Announcement | 33 days out. Announce by 3/17 per contract. Road to DFT angle. Ravehouse venue. | Announce by 3/17 |
| Denver Maintenance | 39 days out. Already announced 1/12. Maintenance phase ads to keep momentum. Expected sellout. | Ongoing |
| Verify All Missing Venues | Tampa, Louisville, Covington, Rochester, Tucson, Dallas, Houston, San Diego all show TBD venues. | ASAP |
| Deposit Status Audit | Verify deposit paid/received for ABQ, Pittsburgh, Louisville, Covington, and all upcoming shows. | By 3/3 |

# Market Intelligence — Upcoming Shows

Integrated from the Take Us To Your Dealer Tour Book. Per-market research, competition analysis, and sellout probability.

### Albuquerque

Strong local bass crowd. Competing show same night — lineup neutralizes threat. Push Mport collaboration hard. Sellout probability: Medium-High.

### Tampa

Active FL bass community. Spring Break = huge attendance potential. Promo groups: Tampa Bass Family. High-visual TikTok + IG content. Sellout probability: Medium-High.

### Pittsburgh

Very active mid-Atlantic rave scene. SideQuest historically strong for bass. WHOiSEE + Dark Matter pairing is optimal. Sellout probability: High.

### Louisville

Midwest market. Needs campus activation + FB group saturation. Support lineup TBD — recommend Dark Matter or Kotrax.

### Covington

KY secondary market, paired with Louisville for back-to-back routing efficiency. Same promo strategy applies.

### Las Vegas

Ravehouse venue. Dancefestopia tie-in massively boosts hype. LED-based teasers perform well. Sellout probability: Medium-High.

### Denver

Top-3 bass market nationally. Larimer Lounge is perfect for DirtySnatcha. $1,500 vs 90% NET = expected sellout. Sub.mission community. Sellout probability: VERY HIGH.

### Rochester

MPORT TMTYL routing. Hotel reimburse after 175 sold. Radius clause in effect.

### Tucson

AB Touring 1 route. Bonus structure in deal — need threshold details.

### Asbury Park

East Coast fans highly active. House of Independents trusted. WHOiSEE + Dark Matter perfect pairing. NYC crossover potential. Sellout probability: Medium-High.

### Hartford

Underserved CT bass demographic. No competing shows expected. Sellout probability: Medium-High.

### Butte

MAD Series show. $5,000 guarantee + travel. Historically strong turnout. Guaranteed audience. Sellout probability: High.

### Oklahoma City

Bamboo Lounge. Needs local promo group activation.

### Dallas

Support slot for Infected Mushroom — massive visibility opportunity. No marketing spend needed from DSR side.

### Houston

Support slot for Infected Mushroom — same as Dallas. Back-to-back weekend.

### San Diego

PeerPop link live. Summer date gives long runway for marketing.

# System Architecture Status

The unified 6-agent system status as of the handoff from Manus to Claude:

| Agent | Domain | Status | Next Step |
| --- | --- | --- | --- |
| Agent 1: A&R | Demo intake, scoring, vote queue | Scaffolded | ar_scoring.py uses random values — needs Spotify/SoundCloud API integration |
| Agent 2: Bookings | Offers, contracts, financials | Scaffolded | show_onboarding.py and show_grading.py need Google Drive MCP for real folder creation |
| Agent 3: Tour Marketing | 4-phase campaigns, CPT | Most Complete | Budget, geo, ad copy skills work. Needs Meta Marketing MCP for live campaign launch. |
| Agent 4: Creative | Assets, flyers, calendars | Designed Only | Tour support grid integration done. Flyer generation + content calendar need build. |
| Agent 5: Promo | Street team, points, DSP | Scaffolded | promo_points.py functional. Needs Meta/TikTok OAuth for post verification. |
| Agent 6: Tech | System integrity, voting | Designed Only | 2/3 vote enforcement, audit logging, MCP health monitoring need full build. |

## Key Data Gaps to Resolve

- Marketing budget per show is not in any JSON file — cannot calculate phase budget allocations without it

- Tour support grid from handoff is for the EFFIN/Capochino leg (Feb 10-28), not the upcoming dates — need updated grid for March+ shows

- Missing venues for Tampa, Louisville, Covington, Rochester, Tucson, Dallas, Houston, San Diego

- Andrew's full contact info still missing (Open Item #9)

- Deposit status unclear for multiple upcoming shows — need verified payment tracking

- No Meta Ads API credentials configured — cannot launch live campaigns yet

- The linked Google Doc (1Fo-ZN_QleSB...) was not accessible — sharing permissions may need updating